## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Placement Prediction Status and Year of Graduation Calculation |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 |  | Data Quality Issues | Data Quality | Yes | Implement data validation checks and cleaning procedures during preprocessing. | Implemented data validation checks and preprocessing improvements. | Data Analyst | Solved | Data quality improved, leading to more accurate calculations.
2 |  | Data Assumptions | Data Assumptions | Yes | Manually select the other data needed for the prediction task instead of asking ML model to automatically select them | Manually selecting the other data need for prediction task. | Data Analyst | Solved | Ensured data assumptions align with actual data.
3 |  | Model Assumptions | Model Assumptions | Yes | Perform model evaluation and be prepared to switch to a different model if necessary. | Conducted model evaluation and switched to an alternative model when required. | Data Scientist | Solved | Improved model performance and accuracy.
4 |  | Data Issues | Data Quality | Yes | Establish data validation processes and address data issues as they arise. | Developed data validation processes and addressed data issues promptly. | Data Analyst | Solved | Data quality maintained throughout the project.
5 |  | Performance Issues | Model Performance | Yes | Continuously monitor model performance and optimize code for efficiency. | Regularly monitored model performance and optimized code for efficiency. | Data Scientist | Solved | Model performance met expectations, and code efficiency improved.